25 June 2026

Terms of Reference for the Procurement of Services

Knowledge Management Expert for CSOs

Charitable Organization “CHARITABLE FUND “RIGHT TO PROTECTION” (hereinafter - the Fund) implements the project “Strengthening Communities through Local Actions and Multisectoral Support in Emergencies in the Southern and Eastern Regions of Ukraine”, which is carried out within the framework of the multi-donor project “Enhancing the Capacity of Communities in the South and East of Ukraine through Local Initiatives (EMPOWER)”, funded by the German Federal Ministry for Economic Cooperation and Development (BMZ), co-financed by the Directorate-General for European Civil Protection and Humanitarian Aid Operations, and implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

One of the project components aims to strengthen the organizational capacity of CSOs working in the field of emergency humanitarian response, with vulnerable categories of the population and IDPs through the implementation of mentoring support and networking for sustainable and effective work.

Vacant vacancy: Knowledge Management Expert for CSOs (hereinafter - the Expert)

Format of service provision: online/hybrid, with readiness for business trips.

Possible participation in off-line educational and presentation events of the project, monitoring visits to CSOs in the following cities: Zaporizhzhia, Mykolaiv, Kherson, Dnipro, Kyiv, Odesa, Lviv.  Maximum number of business trips - 15. Admission to visits will depend on the security situation in the country and upon approval by the Fund’s Security Department.

Service provision period: July 2026 - March 2027.

Number of service providers: within this tender, 1 winner will be selected.

Number of CSOs for work: the project covers 30 CSOs during the project implementation period.

Estimated involvement of the Expert: up to 196 calendar days, where 1 day should not exceed 8 hours.

- Terms of Reference within the provision of services:

| Tasks and duties of the engaged Expert | Result | Service provision period |
| --- | --- | --- |
| Preparation and participation in the introductory session for CSOs. | A program and materials for the introductory session will be prepared in partnership with the organizational development mentor for CSOs and other team members. A group of participants will be gathered (invitations, instructions, etc. will be sent) | July - August 2026 |
| Administration of communication channels/creation of a platform for communication of project participants (Fb community page, What’s Up group): collection and dissemination of information. | Preparation of announcements, materials for dissemination on the Facebook page of the project community, as well as in the What’s Up group. Inclusion of new group members from among representatives of CSOs - project participants. Daily moderation of communication in the group, Q&A. | July 2026 - March 2027 |
| Creation and distribution of an informational and educational bulletin (brochure) on various topics of organizational development of CSOs. | Up to 15 issues of the informational and educational bulletin (brochure) in A4 format, 4 pages, have been created and distributed. This component is implemented in partnership with the organizational development mentor for CSOs and other team members. | July 2026 - March 2027 |
| Organization and technical support of on-line trainings for CSOs, seminars and webinars: preparation of schedules, coordination, booking on-line platforms, photo documentation, preparation of video recordings for the report, development of registration cards, Google Forms questionnaires for assessing the level of knowledge acquisition, etc. | Organized and provided technical support for at least 10 on-line events. | August 2026 - March 2027 |
| Organization and support of off-line trainings for CSOs, seminars, webinars, networking events: preparation of schedules, coordination, development of registration cards, Google Forms questionnaires for assessing the level of knowledge acquisition, collection of documents from participants for reimbursement of travel expenses, preparation of reports and their transfer to the responsible functional departments of the Fund, etc. | Organized and provided appropriate support for at least 10 off-line events at the event sites. | August 2026 - March 2027 |
| Organization and support of individual on-line consultations for CSOs: preparation of schedules, coordination, booking on-line platforms, photo documentation and preparation of video recordings for the report, development of registration cards. | About 400 consultations by about 20 consultants have been organized. This component is implemented in partnership with the organizational development mentor for CSOs and other team members. | July 2026 - March 2027 |
| Collection and systematization of statistical data based on the results of conducted events, preparation of reports, preparation of information upon request of the project manager, donor or other interested parties. | Monthly calculation and updating of statistical data regarding conducted training events, consultations, etc. has been carried out | August 2026 - March 2027 |
| Filling in blocks related to the training component, consultations and other educational events in mentoring reports on organizational development of CSOs, as well as in reports for the donor. | Information has been prepared and the relevant blocks have been filled in about 25 mentoring reports on organizational development of CSOs and 3 reports for the donor. | February - March 2027 |
| Storage, systematization of all materials on the educational component on the corporate Google Drive, as well as filling in the relevant blocks on the project board on the ASANA platform and other CRM systems of the Fund. | Daily updating of data on the Google Drive, the project board on the ASANA platform and other CRM systems of the Fund has been carried out. | July 2026 - March 2027 |
| A final report has been prepared based on the results of the implemented work, which will indicate recommendations for the implementation of the educational component within the Capacity Strengthening Program for local organizations. Also, the report must provide links to all products and materials created within the project. | A final report has been prepared. | March 2027 |
| Performance of other tasks within the educational component upon additional request of the program coordinator, project manager within the engagement and competencies of the Expert provided by the contract. | Tasks have been performed and relevant reports have been prepared | July 2026 - March 2027 |
| Participation in business trips for the purpose of performing assigned tasks. | Participation in no more than 15 business trips. | July 2026 - March 2027 |
| Total involvement of the Expert, days |  | up to 196 |

2. Reporting

The Expert submits an invoice, an act of completed works with the indicated distribution of time for performing tasks, a link to the corporate Google Drive to samples of developed materials that became the basis for payment for the services provided, tables, registers and other products. All materials developed within the framework of project implementation are stored on the corporate drive.

Reports and all supporting materials produced by the Expert within the project are transferred to the Fund without any encumbrance regarding copyright.

The report is submitted monthly or upon the fact of service provision.

3. Terms of cooperation

The tender participant is a private entrepreneur, who submits their proposal for participation in the tender. The Contractor in the context of this tender is the person who will directly provide the services in accordance with the terms of the tender documentation and the concluded agreement.

All settlements are made exclusively in the national currency of Ukraine (hryvnia) by bank transfer to the current account of the individual entrepreneur or legal entity - service provider within 7 working days from the date of approval of the working time sheet and provision of the invoice.

The Fund has the right to accept or reject any proposal or cancel the tender at any time before concluding the agreement with the supplier and bears no responsibility for this.

The participant may at any time, but no later than 2 (two) days before the deadline for submission of tender proposals, contact the Fund for explanations or clarifications regarding the subject of procurement by sending a request letter to the email address: tender@r2p.org.ua.

ATTENTION! The Customer reserves the right to change the volumes of services! The volume of services is determined jointly with the project manager of CF “Right to Protection” and fixed by additional agreements. The preliminary expected volume of services is set out in p. 1 of this tender announcement.

Taxes, fees or payments of the Government of Ukraine, the Government of the Federal Republic of Germany and/or the Governments of any other countries are paid by the Contractor according to the amount received.

Travel/accommodation expenses are reimbursed on the basis of properly executed and project manager-approved supporting documents. Per diems are not paid.

The participant must not be on the sanctions lists of Ukraine, the EU, the USA, Canada, Japan, the United Kingdom.

The participant must not be in the process of termination of activity of the private entrepreneur.

The participant may not be registered as a private entrepreneur at the time of submission of the application, but guarantees to register within 3 days from the date of announcement as the winner of the tender.

- Requirements for submission of proposals

The proposal must be prepared in Ukrainian.

Please provide the following package of documents, which will contain::

- Contact information of the contractor;

- CV with a detailed description of relevant experience for the last 5 years. Please tell in detail about the number and areas of trainings, consultations, seminars, webinars, mentoring sessions that you accompanied as an organizer, how many participants took part, what was the geography of the participants, what topics you worked with, how many events you had to organize simultaneously, whether you organized/conducted on-line and off-line events, what documents you prepared for the specified events, what reports you formed, what on-line platforms you have experience working with (Google Drives, social networks, CRM systems, ZOOM, etc.), whether you have experience cooperating with engaged consultants/trainers, with how many specialists you had to work simultaneously, etc.;

- Letters of recommendation, letters of gratitude from CSOs, business or authorities that relate to the tasks of this project.

- Summing up the results of the competition

The evaluation of tender proposals will consist of 70% evaluation of technical proposals and 30% evaluation of price proposals.

| SCALE FOR EVALUATION OF TECHNICAL REQUIREMENTS |  |  |  |
| --- | --- | --- | --- |
|  | Criteria | EVALUATION METHODOLOGY | Maximum number of points for the requirement |
| 1 | The Contractor must have higher education. | 5 points: Master, Specialist in the fields of communications, marketing, management, management of non-profit organizations, public management and administration, legal sciences or other humanities, finance, economics, etc. 3 points: Bachelor in the fields of communications, marketing, management, management of non-profit organizations, public management and administration, legal sciences or other humanities, finance, economics, etc. 0 points: Absence of higher education OR no information on education or copies of diplomas provided OR the education of the Contractor is completely irrelevant to the Customer’s requirements. | 5 |
| 2 | CV. The participant must provide a detailed CV of the Contractor. The content of the CV is assessed with indication of experience, acquired skills. | 15 points: Demonstration of detailed information in the key areas and tasks of the request, a detailed description of powers, skills, achievements, developed materials, conducted trainings/webinars/training sessions during the period of acquiring experience is indicated. Information is provided on the number and areas of trainings, consultations, seminars, webinars, mentoring sessions that the Contractor accompanied as an organizer, how many participants took part, what was the geography of participants, what topics they worked with, how many events they had to organize simultaneously, whether they organized/conducted on-line and off-line events, what documents they prepared for the specified events, what reports they formed, what on-line platforms they have experience working with (Google Drives, social networks, CRM systems, ZOOM, etc.), whether they have experience cooperating with engaged consultants/trainers, with how many specialists they had to work simultaneously, etc. The CV is updated and contains information on the expert’s activities for at least the last 5 years. 8 points: Demonstration of generalized information in the key areas and tasks of the request. Work experience and key areas of performance are indicated without additional details about skills, achievements or developments, volumes of work and results, etc. The CV is updated and contains information on the expert’s activities for at least the last 3 years. 3 points: A CV has been provided with the absence of current experience for the last 3 years in the areas and tasks of the request, but reflects the existing previous experience of the contractor in performing similar tasks. 0 points: No CV provided or the experience is not relevant to the area and tasks of the request. | 15 |
| 3 | Interview The Contractor took part in an interview (interview) | 15 points: The Contractor joined the meeting on time, is familiar with the subject of the tender announcement, clearly answers questions regarding experience working with CSOs, experience in conducting and supporting training and other educational programs. The Contractor has public communication skills, speech without filler words, offensive statements, free communication in Ukrainian, etc. Has significant experience in technical support of on-line trainings/webinars/seminars, knows how to use the most popular on-line platforms ZOOM, Teams, Google Meet, as well as social networks and messengers (facebook, what`s up). The Contractor demonstrates the ability to manage interaction with a large number of participants in the educational process and consultations. 10 points - The Contractor joined the meeting, is familiar with the subject of the tender announcement, clearly answers questions regarding experience working with CSOs, experience in conducting and supporting training and other educational programs. However, the available experience is not significant, or partial, the contractor did not independently implement all processes provided for by the terms of reference. The Contractor has poor/no public communication skills, formulates sentences in a complicated, incoherent manner, speech with filler words, offensive statements, etc. Poor command of spoken Ukrainian. Insignificant experience in technical support of on-line trainings/webinars/seminars, does not know how/or knows but uses the most popular on-line platforms ZOOM, Teams, Google Meet, as well as social networks and messengers (facebook, what`s up) uncertainly. The Contractor does not demonstrate the ability to manage interaction with a large number of participants in the educational process and consultations. 6 points - The Contractor joined the meeting, is familiar with the subject of the tender announcement, has indirect /does not have experience working with CSOs, experience in conducting and supporting training and other educational programs. The Contractor’s answers are of a generalized nature. The Contractor has poor/no public communication skills, formulates sentences in a complicated, incoherent manner, speech with filler words, offensive statements, etc. Poor command of spoken Ukrainian. No/or little experience in conducting on-line trainings, managing social networks and professional communities in messengers, etc. The Contractor has no experience interacting with a large number of participants in the educational process (trainers, consultants, beneficiaries). Has no experience in independently performing most of the points from the terms of reference. 3 points - The Contractor joined the meeting, is superficially familiar with the subject of the tender announcement, answers to questions are of a generalized nature without providing specific and clear answers. The Contractor does not have public communication skills, speech is saturated with filler words, offensive statements, obscene jokes, etc. Poor command of spoken Ukrainian. Has insignificant/does not have experience in implementing most of the points of the terms of reference. 0 points - The Contractor did not join the meeting, or does not possess information about the subject of the tender announcement, or cannot answer questions on the topic. | 15 |
|  | The Contractor provided materials that that confirm the experience indicated in the CV | 15 points - The Contractor provided a large number of materials that maximally confirm the experience regarding conducting/supporting trainings/webinars/seminars/consultations: presentations, instructions, screenshots of social media pages/groups in messengers, templates of documents for supporting consultations, etc. 8 points - The Contractor provided an insignificant number of materials that very indirectly confirm the Contractor’s competencies regarding conducting/supporting trainings/webinars/seminars/consultations. 0 points - The Contractor did not provide any materials, or the materials provided are not relevant to the topic of the request or do not confirm the Contractor’s competencies to perform the specified tasks. | 15 |
| 4 | The Contractor has experience working in the civic sector | 10 points - The Contractor has significant experience cooperating with CSOs, in particular experience in conducting/supporting trainings specifically for CSOs, taking into account the needs and specifics of the non-profit sector. Held positions of educational programs manager/knowledge management expert, project manager, specialist of the personnel professional development department, trainer, etc. 7 points - The Contractor has significant experience cooperating with CSOs, however this experience is not relevant to the topic of the request. The Contractor did not work with the educational component. 5 points - The Contractor has insignificant experience cooperating with CSOs or the existing experience is not relevant to the topic of the request, etc. The Contractor did not hold positions related to implementation of educational events, project management, improvement of staff competencies, etc. 0 points - The Contractor did not work with CSOs. | 10 |
| 5 | The Contractor has experience in selecting trainers, mentors, consultants for training programs | 10 points - The Contractor has significant experience developing tender announcements, conducting interviews and selecting trainers/consultants/mentors, taking into account the needs and specifics of the non-profit sector. 5 points - The Contractor has little experience in selecting trainers/consultants/mentors or did not conduct the full cycle independently. 0 points - The Contractor has no experience in preparing tender documents and selecting trainers/consultants/mentors. | 10 |