25 February 2026

Technical specifications for the procurement of online training services on the topic

DIGITAL TOOLS FOR ONLINE EVENTS: ORGANISATION AND CONDUCT OF TRAINING COURSES AND WEBINARS, GROUP CONSULTATIONS, ETC.

Charitable organisation "CHARITABLE FOUNDATION "RIGHT TO PROTECTION" (hereinafter referred to as the Fund) is implementing the project “Strengthening Communities through Localized Action and Multisectoral Emergency Support in South and East regions of Ukraine” is carried out within the multi-donor project “Strengthening Communities in War-Affected Regions in Ukraine through Localized Action (EMPOWER),” which is funded by the German Federal Ministry for Economic Cooperation and Development (BMZ) with co-financing from the Directorate-General for European Civil Protection and Humanitarian Aid Operations and implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

The project aims to strengthen the organisational capacity of CSOs working in the field of humanitarian response with vulnerable populations and IDPs through the implementation of mentoring and networking for sustainable and effective work.

Service being procured: online training in a modular format.

Service delivery format: online.

Service provision period: March-April 2026 (tentative start date: 23 March 2026). The training is conducted in the format of a series of interrelated online training sessions (modules) that are components of a single training course.

Geography of project participants: Zaporizhzhia, Mykolaiv, Odesa, Kherson, Lviv, Ivano-Frankivsk, Kyiv, Poltava, Sumy, Kharkiv and Dnipropetrovsk regions.

Number of service providers: 1 winner will be selected within this LOT.

Number of CSOs to work with: the project covers 25 CSOs from the second wave.

Number of training participants: up to 50 people

Duration of training: up to 15 hours in total.

The online training is conducted as a single training event in a modular format and includes a series of interrelated online sessions, independent study of materials by participants between sessions, verification of completed tasks by the trainer, and feedback. The amount of time for online sessions and feedback is proposed by the trainer in Appendix 1 Description of the vision for the implementation of the technical task.

The amount of time for training preparation, accompanying materials and reporting is determined independently by the service provider. The cost of these services must be included in the total price for the provision of services.

A detailed list of tasks is provided in section 1 Technical task within the scope of service provision.

- Technical task within the scope of service provision LOT 3:

| No | No | Task | Technical characteristics of the final product | Result | Period of service provision |
| --- | --- | --- | --- | --- | --- |
| 1 | 1 | Develop an online training programme (modular format) | Word document with a training programme consisting of 5 training modules (sessions) | An online training programme has been developed, specifying the topics of each session, the logic of the training sequence and the expected results | 14 days before the training date |
| 2 | 2 | Develop the training schedule | Word document with the training schedule in accordance with the programme | Detailed training schedule with a minute-by-minute breakdown of time for each item on the programme | 14 days before the training date |
|  | 3 | Develop questions for the knowledge assessment questionnaire (pre- and post-training assessment) | Word document with a list of questions/closed questions/answer options | A list of questions for pre- and post-training questionnaires to assess the level of knowledge acquisition by training participants has been created and provided to the project team | 14 days before the training date |
| 4 | 4 | Develop handouts (notes) on the training topic | Electronic document in Word or PDF format | Prepare structured handouts for training participants and submit them to the project team | 14 days before the training date |
| 5 | 5 | Prepare presentations for online training sessions | Presentations in PowerPoint format using the project template | Presentation materials prepared for each training session, covering all topics of the programme and meeting the visual requirements of the project | 14 days before the training date |
| 6 | 6 | Develop practical tasks for participants, including for independent study | File with a description of practical tasks, case studies and instructions for their completion | Develop practical tasks to be completed during online sessions and inter-session tasks for independent study | 14 days before the training date |
| 8 | 7 | Conduct online training (modular) | Conduct a series of online sessions on the ZOOM platform. During the training, presentations and practical tasks were used, and handouts were provided to participants | Online training conducted in a modular format in accordance with the agreed programme, using presentations, practical tasks, interactive teaching methods and discussions | March-April 2026 (tentative start date: 23 March 2026). |
|  | 8 | Check the tasks completed by participants for independent study and provide feedback. | Electronic file/comments with the results of the check | Participants' homework assignments were checked and individual or general feedback was provided on their level of understanding of the material | during the training period |
| 9 | 9 | Provide methodological support to participants between sessions | Online consultations (as needed), communication regarding task completion | Participants received explanations of the tasks for independent study and support during the learning process | during the training period |
|  | 10 | Prepare a final report on the results of the training | A report on the training was provided using the template provided by the Foundation. | A final report was provided containing a brief description of the sessions held, CSO participation, analysis of learning outcomes and general recommendations | No later than 5 working days after the end of the training |

- Reporting

The contractor shall submit reports on the implementation of the Technical Assignment in accordance with the technical specifications and the template provided by the customer.

All services and products must be provided in Ukrainian and sent by post. y.honchar@r2p.org.ua

Reports and all accompanying materials produced by the Contractor under the contract shall be transferred to the Fund without any copyright restrictions.

- Terms of cooperation

The tender participant is an individual entrepreneur (hereinafter referred to as IE) who submits their proposal to participate in the tender. The Contractor in the context of this tender is the person who will directly provide services in accordance with the terms of the tender documentation and the concluded contract. Agencies operating as LLCs are also eligible to participate in the tender.

Payment shall be made upon completion of the work for the services actually provided on the basis of the signed Agreement, original invoices, the act of acceptance and transfer of the services provided, and a report containing samples of the developed materials.

All payments shall be made exclusively in the national currency of Ukraine (hryvnia) by bank transfer to the current account of the individual entrepreneur - service provider within 7 working days from the date of submission of the act of work performed, invoice for payment and report.

The Fund has the right to accept or reject any proposal or cancel the tender at any time prior to the conclusion of the agreement with the supplier and shall not be liable for this.

At any time, but no later than 2 (two) days before the deadline for submitting tender proposals, the participant may contact the Fund for clarification or clarification regarding the subject of the procurement by sending a letter with a request to the email address: tender@r2p.org.ua.

ATTENTION! The customer reserves the right to change the scope of services! The scope of services is determined jointly with the project manager of the Right to Protection Charitable Foundation. The preliminary expected scope of services is set out in paragraph 1 of this tender announcement.

Taxes, fees or payments to the Government of Ukraine and/or the governments of any other countries shall be paid by the Participant in accordance with the amount received.

The Participant must not be on the sanctions lists of Ukraine, the EU, the USA, Canada, Japan or the UK.

The Participant must not be in the process of terminating its sole proprietorship.

- Requirements for submitting proposals

The proposal must be written in Ukrainian.

Please provide the following package of documents, which shall include:

- Contact information of the tender participant and service provider (if different);

- The service provider's CV with a detailed description of relevant experience over the last 3 years;

- Samples of developed materials (presentations for online training, training programmes, handouts and methodological materials, etc.). Submit in pdf, word, excel, Power Point or other formats that are accessible for general viewing;

- Appendix 1 Description of the vision for the implementation of the technical task (at least 1.5 pages of text, Times New Roman font, 11) in pdf format with signature and stamp, if available;

- Appendix C. (Price proposal.) The price proposal must be submitted in the established form using the Ukrainian hryvnia as the currency. The price proposal must be signed and stamped, if available. The participant independently determines the price for the services that they offer to provide under the Procurement Agreement. Additional services and expenses that have not been agreed upon and provided for in the Contract shall not be paid for;

- Letters of recommendation, letters of appreciation from CSOs, businesses or authorities related to the tasks of this project.

- Scanned copies of registration documents (documents issued by authorised authorities confirming the registration of the tender participant in Ukraine as an individual entrepreneur (IE Group 3)).

5. Summing up the results of the competition

The evaluation of tender proposals will consist of 70% evaluation of technical proposals and 30% evaluation of price proposals.

| TECHNICAL REQUIREMENTS EVALUATION SCALE |  |  |  |
| --- | --- | --- | --- |
|  | Evaluation criteria | EVALUATION METHODOLOGY | Maximum number of points per requirement |
| 1 | Level of education. In the best and acceptable scenario, the Contractor is expected to have a higher education degree not lower than a bachelor's degree in the fields of communications, marketing, management, non-profit organisation management, public management and administration, law or other humanities, finance, economics. | 5 points - Master's degree, Specialist in the fields of communications, marketing, management, non-profit organisation management, public management and administration, legal sciences or other humanities, finance, economics. 3 points - Bachelor's degree in communications, marketing, management, non-profit organisation management, public management and administration, legal sciences or other humanities, finance, economics. 0 points - No higher education OR no information provided on education or copies of diplomas OR the Contractor's education is completely irrelevant to the Customer's requirements. | 5 |
| 2 | Resume. The participant must provide a detailed CV of the Contractor. The CV is evaluated for content, indicating experience and skills acquired. | 10 points - Demonstration of comprehensive information in key areas and tasks of the request, detailed description of powers, skills, achievements, developed materials, conducted trainings/webinars/training sessions during the period of experience acquisition. The CV is up to date and contains information on the specialist's activities for at least the last 5 years. 8 points - Demonstration of generalised information in key areas and tasks of the request. Work experience and key areas of performance are specified without additional details about skills, achievements or developments. The CV is up to date and contains information about the specialist's activities for at least the last 3 years. 5 points - A CV has been provided with no relevant experience over the last 3 years in the areas and tasks of the request, but the contractor's previous experience in performing similar tasks is reflected. 0 points - No CV provided or experience is not relevant to the field and tasks of the request. | 10 |
| 3 | Developed materials. The participant must submit samples of developed materials (presentations, training programmes, handouts and methodological materials, etc.). | 15 points - the materials provided correspond to the topic of the request and reflect the performer's experience in the topic of the request. 10 points - the materials provided are indirectly related to the topic, but demonstrate the contractor's ability to perform similar tasks. 8 points - the materials provided are not related to the topic of the request, but demonstrate the contractor's ability to perform similar tasks. 5 points - the materials provided are not related to the topic of the request or do not demonstrate the contractor's ability to perform similar tasks. 0 points - no materials were submitted. | 15 |
| 4 | Description of the vision for the implementation of the technical task. The participant must submit a description of their vision for the implementation of the technical task (Appendix 1). | 15 points - the materials provided correspond to the topic of the request and reflect the contractor's experience in the topic of the request and a high level of professionalism/expertise. 12 points - the materials provided correspond to the topic of the request and reflect the contractor's experience in the topic of the request. However, the materials show an average/or low level of professionalism/expertise. 10 points - the materials provided are indirectly related to the topic, but demonstrate the contractor's ability to perform similar tasks. 8 points - the materials provided are not relevant to the topic of the request, but demonstrate the contractor's ability to perform similar tasks. 5 points - the materials provided are not related to the topic of the request or do not demonstrate the contractor's ability to perform similar tasks. 0 points - no materials were submitted. | 15 |
| 5 | Interview. The participant took part in an interview | 15 points: the participant arrived on time for the meeting, is familiar with the subject of the tender announcement, clearly answers questions about their experience working with CSOs, experience in developing training programmes and conducting training sessions, etc. The participant has public speaking skills, speaks without filler words or offensive statements, communicates fluently in Ukrainian, etc. Has significant experience in conducting offline training sessions. 10 points - the participant joined the meeting, is familiar with the subject of the tender announcement, clearly answers questions about their experience working with CSOs, experience in developing training programmes and conducting training sessions, etc. However, the participant has poor/no public speaking skills, formulates sentences in a complex, incoherent manner, uses filler words, offensive statements, etc. Poor command of spoken Ukrainian. No/little experience in conducting offline training sessions, etc. 8 points - the participant joined the meeting, is familiar with the subject of the tender announcement, has indirect/no experience working with CSOs, developing training programmes and conducting training sessions, etc. The participant has poor/no public speaking skills, formulates sentences in a complex, incoherent manner, uses filler words, offensive statements, etc. Poor command of spoken Ukrainian. No/little experience in conducting offline training, etc. 5 points - the participant joined the meeting, is superficially familiar with the subject of the tender announcement, and answers questions in a generalised manner without providing specific and clear answers. The participant lacks public speaking skills, their speech is saturated with filler words, offensive statements, inappropriate jokes, etc. Poor command of spoken Ukrainian. 0 points - the participant did not attend the meeting, or does not have information about the subject of the tender announcement, or cannot answer questions on the topic. | 15 |
| 6 | Experience of cooperation with civil society organisations. The participant has experience in providing services to civil society organisations. | 10 points - The participant has significant experience of cooperation with CSOs, in particular experience of conducting training specifically for CSOs, taking into account the needs and characteristics of the non-profit sector. 5 points - The participant has limited experience of cooperation with CSOs, and the existing experience is not relevant to the subject of the request, etc. 0 points - The participant has not worked with CSOs. | 10 |